## Prabhjot Kaur
To-do list
To be completed by: |  |  |  | Name Prabhjot Kaur
Deadline: |  |  |  | Date 5/17
Project 2.5
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Notes | Column1 | Column2 | Column3
100% | Planning - Figuring Roles | 2026-05-14 | 2026-05-14 |  | 1 day | assigned work to each members
100% | Preparation - Communicating with others | 2026-05-14 | 2026-05-14 |  | 1 day | Discussed with Frankie about work distribution within group members
100% | Add/remove columns for normalization | 2026-05-15 | 2026-05-16 |  | 2 days | dropped and added some columns to make it look (cleaner) normalized.
100% | Create Process.WorkflowSteps table | 2026-05-15 | 2026-05-16 |  | 2 days | Created schema and table in the database
100% | Assist others if groupmates are unavailable | 2026-05-15 | 2026-05-17 |  | 3 days | Gave reminders about deadlines and assisted with instructions and tasks.
100% | Create a .bak backup file of the final database | 2026-05-17 | 2026-05-17 |  | 1 day
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days | pushed file in github
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Frankie | 2026-05-16 | 2026-05-17 |  | 2 days | communicated effectively -FL

## Salvador Cardoso
To-do list
To be completed by: |  |  |  | Name Salvador Cardoso
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning - Understanding project | 2026-05-13 | 2026-05-14 |  | 2 days
100% | Preparation - Creating a summary of tasks | 2026-05-13 | 2026-05-14 |  | 2 days
100% | First draft of UDTs | 2026-05-14 | 2026-05-15 |  | 2 days
100% | Add constraints to every table | 2026-05-14 | 2026-05-16 |  | 2 days
100% | Assist others if groupmates are unavailable | 2026-05-15 | 2026-05-17 |  | 3 days
100% | Finish up UDTs | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Frankie or Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days | communicated effectively -FL

## Frankie Liang
To-do list
To be completed by: |  |  |  | Name Frankie Liang
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning - Assigning tasks | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Preparation - Creating Repo and proper files/directories | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Creating ToDoList planner with all due dates and tasks | 2026-05-14 | 2026-05-14 | 2026-05-15 | 1.5 days | Finished late at night into the morning but communicated initial tasks verbally
100% | Add/remove columns for normalization | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Create Process.WorkflowSteps table | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Accomplish tasks if not handled appropriately or in a timely manner by groupmates | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days

## Kanwal Jit Singh
To-do list
To be completed by: |  |  |  | Name Kanwal Jit Singh
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By2 | Revised Due By | Number Of Days | Revision Notes
100% | Planning - looking at project specifications | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Preparation | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Create UDTs for all columns | 2026-05-15 | 2026-05-15 |  | 2 days
100% | Add constraints to every table | 2026-05-15 | 2026-05-15 |  | 2 days
100% | PowerPoint Presentation | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Video | 2026-05-16 | 2026-05-17 |  | 2 days
0% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
0% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days | wasnt notified of anything -FL
0% | Follow-up with Frankie or Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days | did not communicate -FL

## Simran Singh
To-do list
To be completed by: |  |  |  | Name Simran Singh
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning - looking at project specifications | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Preparation | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Convert yellow-highlighted tables to views/TVFs | 2026-05-15 | 2026-05-16 |  | 2 days
90% | Design & document indexes | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Create a full PDM showing all tables, foreign keys, and cardinality , organize it by subject areas | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Include UDTs as part of the PDM diagram | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Frankie or Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days | communicated effectively -FL

## Brandon Cho
To-do list
To be completed by: |  |  |  | Name Brandon Cho
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning - looking at project specifications | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Preparation - Communicating and understanding role | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Convert yellow-highlighted tables to views/TVFs | 2026-05-15 | 2026-05-16 |  | 2 days
90% | Design & document indexes | 2026-05-15 | 2026-05-16 |  | 2 days
100% | PowerPoint Presentation | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Video | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Frankie or Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days | communicated effectively -FL

## Amrina Qayyum
To-do list
To be completed by: |  |  |  | Name Amrina Qayyum
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning - Creating a summarization on tasks | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Preparation - Creating an example project as a basis through AI | 2026-05-14 | 2026-05-14 |  | 1 day
90% | Identify data anomalies | 2026-05-15 | 2026-05-16 |  | 2 days
90% | Correct anomalies & document strategy | 2026-05-15 | 2026-05-16 |  | 2 days
75% | Add anything additional to differentiate your group's presentation from the others | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Create a .bak backup file of the final database | 2026-05-17 | 2026-05-17 |  | 1 day
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Frankie or Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days | communicated effectively -FL

## Shuai Wang
To-do list
To be completed by: |  |  |  | Name Shuai Wang
Deadline: |  |  |  | Date 5/17
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning - looking at project specifications | 2026-05-14 | 2026-05-14 |  | 1 day
100% | Preparation | 2026-05-14 | 2026-05-14 |  | 1 day
90% | Identify data anomalies | 2026-05-15 | 2026-05-16 |  | 2 days
90% | Correct anomalies & document strategy | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Create a full PDM showing all tables, foreign keys, and cardinality , organize it by subject areas | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Include UDTs as part of the PDM diagram | 2026-05-15 | 2026-05-16 |  | 2 days
100% | Paperwork - GITHUB | 2026-05-15 | 2026-05-17 |  | 2 days
100% | Hand-off | 2026-05-16 | 2026-05-17 |  | 2 days
100% | Follow-up with Frankie or Prabhjot | 2026-05-16 | 2026-05-17 |  | 2 days | communicated effectively -FL