## Prabhjot Kaur
To-do list
To be completed by: |  |  |  | Name Prabhjot Kaur
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Send to group mate to Combine group work
100% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video

## Salvador Cardoso
To-do list
To be completed by: |  |  |  | Name Salvador Cardoso
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Send to group mate to Combine group work
100% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video

## Frankie Liang
To-do list
To be completed by: |  |  |  | Name Frankie Liang
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work to Group mates
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Combine group work
87.5% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Could not get into contact with last group member other than providing the repo

## Kanwal Jit Singh
To-do list
To be completed by: |  |  |  | Name Kanwal Jit Singh
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Send to group mate to Combine group work
100% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video

## Simran Singh
To-do list
To be completed by: |  |  |  | Name SImran Singh
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Send to group mate to Combine group work
100% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video

## Slvador Cardoso
To-do list
To be completed by: |  |  |  | Name Slvador Cardoso
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Send to group mate to Combine group work
100% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video

## Shuai Wang
To-do list
To be completed by: |  |  |  | Name Shuai Wang
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
50% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Combine group work
0% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video

## Amrina Qayyum
To-do list
To be completed by: |  |  |  | Name Amrina Qayyum
Deadline: |  |  |  | Date 4/23/2026
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 04/16/2026 | 04/16/2026 | 04/16/2026 | 1 | Divide work
100% | Preparation | 04/16/2026 | 04/17/2026 | 04/17/2026 | 1 | Setup tools
100% | Task a | 04/17/2026 | 04/17/2026 | 04/17/2026 | 1 | Take a protion of SQL propositions to solve
100% | Task b | 04/18/2026 | 04/18/2026 | 04/18/2026 | 1 | Write SQL queries
100% | Task c | 04/18/2026 | 04/19/2026 | 04/19/2026 | 1 | Documentation/Test queries
100% | Task d | 04/19/2026 | 04/20/2026 | 04/20/2026 | 1 | Excel, powerquery
100% | Paperwork | 04/20/2026 | 04/21/2026 | 04/21/2026 | 1 | Video
100% | Hand-off | 04/22/2026 | 04/22/2026 | 04/22/2026 | 1 | Combine group work
100% | Follow-up | 04/23/2026 | 04/23/2026 | 04/23/2026 | 1 | Submit files, video